## START
Click here to enter a new item to your Genebank Risk Management REGISTER

## RiskRegister
RISK ID | GENERAL AREA : Activity | Risk Source | Consequence 1 | Consequence 2 | Consequence 3 | Consequence 4 | Consequence 5 | Risk Owner | Likelihood Level | Germplasm | Information | People | Environment | Asset/Facility | operations | Legal | Reputation | Adjustment Factor | Adjustment Factor DESCRIPTION | Risk Rating | Risk Level

## RiskManagement
RISK ID | GENERAL AREA : Activity | Risk Source | Risk Owner | Risk Level | Action Plan: People | Action Plan: Facility | Action Plan: Procedure | Contingency

## LISTs (hidden)
Acquisition: Collecting | Acquisition: Donation | Conservation: Registration | Conservation in vitro: Sample Processing | Conservation in vitro: Germplasm Testing | Conservation in vitro: Conservation Procedure | Conservation in vitro: Storage Facility | Conservation in vitro: Safety Duplication | Conservation in vitro: Regeneration | Conservation in Cryo: Sample Processing | Conservation in vitro: Germplasm Testing | Conservation in vitro:Conservation Procedure | Conservation on field banks: Sample Processing | Conservation on field banks: Germplasm Testing - Health Diagnosis | Conservation on field banks: Germplasm Testing - Storage Monitoring | Conservation on field banks: Conservation Procedure | Conservation on field banks: Field Bank Specifications - Field Monitoring | Conservation on field banks: Field Bank Specifications - Field Planting | Conservation on field banks: Field Bank Specifications - Field Maintenance & Management | Conservation on field banks: Field Bank Specifications - Post harvest Handling | Conservation on field banks: Characterization and Evaluation | Distribution: Policies | Distribution: User Service | Distribution: Germplasm Preparation and Dispatch | Information Management and Dissemination | Infrastructure / Physical Facility: Safety Duplication | Personnel and Support Services | 1 |  | Narrow genetic variability and large gaps in germplasm collection | Failure to capture diversity in field | Send Center genebank personnel to take the lead in joint collecting missions with national programs. Conduct training of collectors in partner countries. Maintain and hire a pool of expert collectors. |  | Analyse collection for un-represented regions and conduct gap-filling collecting. | Send a follow-up collecting mission. | GRU | Consequence
Narrow genetic variability and large gaps in germplasm collection | Received foreign materials carry pests and diseases | Unverified passport and other data submitted | Untrained or inefficient personnel in sample processing | Untrained personnel in health testing of propagules | Errors in media preparation | Unsterile transfer facilities | Safety duplication site is vulnerable to natural calamities | Regeneration failure | Incorrectly identified material is stored | Thawing/rewarming is done improperly | Dewars may fail. | Low initial quality of explants. | Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials | Limited numbers of viable plants | Inadequate selection, pre-conservation or pre-treatment of propagules | Unsuitable conditions in conservation site | Pollen exchange with plants within and outside collection. | Mixtures of fruits and germplasms | Persistence of disease organisms and insects after harvest | Inefficient and erroneous data gathering and encoding | Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty | Germplasm distributed are weak | Misclassification and wrong characterization and germplasm stocks data | Inefficient recording and database management | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Inadequate complement of technical staff | 2 |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | People
Untrained personnel in collecting and documentation | Limited germplasm testing capability | Received materials have low viability | Source of material is infected | Improper screening methods and monitoring regime | Ineffective pre-treatment | Unsuitable tissue culture containers for in vitro samples |  |  | Isolation of material is not done correctly, meristems are damaged and regrowth as callus | Water bath may be contaminated | Unreliable supply of liquid nitrogen (LN) | Improper conditioning and propagation of vegetative material | Ineffective screenhouse to control insects | Mechanical mixtures or invasive plants | Failure in propagation and storage of propagules | High pest and disease pressure in field site | Misidentification | Poor adaptation | Mishandling | Descriptors that have no clear-cut correspondence to current international standard descriptors | Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm |  | Inefficient and slow processing of requests for samples. | Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation) | Poor organization of storage trays, shelves and compartments | Incompetent staff | 3 |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Facility
Misidentification of germplasm | Reluctance to share germplasm due to IP rights | Limited storage space for clonal materials | Poor quality and/or suboptimal size of propagule | Microbes and pests are not apparent at initial testing but appear later. | Chemical imbalance during culture | Poor laboratory maintenance |  |  | Chemical cryoprotectants injure plant cells during pre-treatment | New material in cryo-collection is not viable | Rapid loss of LN in dewar | Failure in propagation and storage of propagules | Backlogs in pest and disease monitoring | Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases) | Inadequate number of replicates per accession. |  | Mixtures of clones | Disparate location of physiologically similar accessions |  | Limited text-based description | Plant health restrictions of importing country |  | Errors in preparing or labeling samples | Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data. | Deterioration of facilities and equipment | Routine tasks and uncompetitive remuneration | Low |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Procedure
Lack of simple collection protocol and documentation forms | Working collections not duplicated in major genebanks |  | Weak mother plants | Untrained personnel in transgene detection | Suboptimal culture methods for a broad range of genotypes |  |  |  | Plants are sensitive to preculture method |  | Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals |  | False positive and false negative results during plant health testing. |  |  |  | Contamination with volunteer plants. | Poor management of weeds and low soil fertility |  | Lack of diversity assessment of collection | Non compliance with phytosanitary regulations |  | Insufficient germplasm stock for distribution | Lack of adequate information about important characteristics of each accession. | Cold room malfunction | Exposure to occupational hazards | Medium |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Contingency
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events |  |  | Ineffective pest and disease screening procedures during sample processing | Inadvertent presence of transgene | Short storage life of propagules |  |  |  | Technique does not work for all plants in the collection |  | Compromised integrity of cryovials | [11 empty] | Bulky tissue-cultured explants | Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container. | Power supply cut-off | Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN. | High |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Responsible Unit
Strict country and international laws on access and use of germplasm |  |  | No efficient tissue sterilisation procedures | Lack or improper determination of transgene presence | Delayed inventory | [5 empty] | Insuffiicent number of stored propagules | [11 empty] | Unfavorable conditions during transport | Lack of secure back-up | Theft or vandalism | Inefficient human resources services |  |  | Narrow genetic variability and large gaps in germplasm collection
Breach of country and international treaties |  |  | Lack of proper disposal procedures of contaminated plant materials | Limited quantity of high quality propagules | Late subculturing | [18 empty] | Important data and information remain in unuseful form. | Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire | Inefficient purchasing and repair services |  |  | Narrow genetic variability and large gaps in germplasm collection
Ambiguous position of countries regarding international treaties |  |  | Ineffective thermotherapy procedure | Ineffective sterilization techniques | Backlog in regeneration | [18 empty] | Outdated or inaccessible procedures manual | Safety duplication site is vulnerable to natural calamities | High cost of genebank operations |  | 0 | Narrow genetic variability and large gaps in germplasm collection
|  |  | Inappropriate media and conditions for culture initiation | Misapplication of antibiotics | [19 empty] | Inconsistent protocols | Changing policies, financial and technical capabilities of governments hosting safety duplication |  |  |  | Narrow genetic variability and large gaps in germplasm collection
|  |  |  | Somaclonal variation | [19 empty] | Lack or complicated tracking and inventory system |  |  |  |  | Untrained personnel in collecting and documentation | Failure to capture diversity in field and document important information | Send Center genebank personnel to take the lead in joint collecting missions with national programs. Conduct training of collectors in partner countries. Maintain and hire a pool of expert collectors. |  |  | Based on level of risk and of diversity in collecting site to target germplasm, send a follow-up collecting mission. | GRU
[24 empty] | Insufficient data on accession identity and culture conditions |  |  |  | 0 | Untrained personnel in collecting and documentation
[24 empty] | Limited ICT capability; server, network and IT related problems |  |  |  |  | Untrained personnel in collecting and documentation
[24 empty] | Malfunctioning equipment, hardware and software problems |  |  |  |  | Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
[29 empty] | Misidentification of germplasm | Misleading information | Include taxonomists during collecting. |  |  | Use molecular methods to verify identity. Invite taxonomists and other experts to verify identity of ambiguous materials. | GRU
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
[29 empty] | Lack of simple collection protocol and documentation forms | Failure to capture diversity in field |  |  | Develop simple collecting procedures and forms. |  | GRU
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
[29 empty] | Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events | Loss of germplasm in habitat |  |  | Prioritize affected areas if containing germplasm that can fill gaps in collection. |  | GRU
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
[29 empty] | Strict country and international laws on access and use of germplasm | Poor access and use of germplasm in unexplored areas |  |  | Secure a Germplasm Acquisition Agreement between donor country and Centre to manage accessions under FAO conditions. | Arrange for unrestricted use with new leaders of donor countries. Acquire material through friendly 3rd party countries. Offer technical incentives. | GRU
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
[29 empty] | Breach of country and international treaties | Legal consequences. Damaged reputation and relationship | Training of all institute staff on intenationally agreed protocols, in consultation with Genebank and other Center authorities. |  | Follow national procedures of obtaining collecting permits, under relevant international agreements. • Collect in partnership with local PGR people. | Keep acquired material under restricted use and access, and seek de-restriction with donor country. | Center top mgt; new employees orientation;GRU
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
[29 empty] | Ambiguous position of countries regarding international treaties | Poor access and use of germplasm in unexplored areas |  |  | Foster goodwill through PGR, pre-breeding, breeding and Treaty-related training-workshops, and incentivize donation. | Help build capacity of national bodies in germplasm collecting. | Center partnership and collaboration office, GRU
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
[29 empty] | Received foreign materials carry pests and diseases | Introduction of pest and diseases to host country |  |  | Strictly observe quarantine regulations. Keep from main storage areas until fully checked and decontaminated. Grow and regenerate materials in screenhouse or away from large crop production areas of local farms. | Confine affected areas, discontinue planting of crop and eliminate other hosts in adjacent areas. | GRU; Germplasm Health unit
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
[29 empty] | Limited germplasm testing capability | Restricts international germplasm exchange |  | Develop testing and handling capability for pests and diseases of international importance. |  |  | GRU; Germplasm Health unit
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
Limited germplasm testing capability
[29 empty] | Reluctance to share germplasm due to IP rights | Restricts international germplasm exchange |  | Conduct training on benefits and limitations of IP rights. |  |  | GRU
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
[29 empty] | Working collections not duplicated in major genebanks | Failure to capture elite germplasm |  |  | Proactively conserve breeding materials. |  | GRU
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
[29 empty] | Unverified passport and other data submitted | Incorrect or unreliable passport data, and poor quality of scientific reports |  |  | Verify passport information with donor. | Classify accessions as ‘tentative’ until standard characterization, etiology and DNA analysis establish their identity. | GRU
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
[29 empty] | Received materials have low viability | Loss of germplasm |  |  | Obtain large amount of samples and handle properly. | Seed increase immediately. | GRU
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
[29 empty] | Limited storage space for clonal materials |  |  |  | Priority materials for in-vitro clonal collection: a) cultivars and elite breeding lines b) clones from center of origin (tetrapoids and diploid forms) c) clones from secondary centers of diversity d) clones with unique characteristics and/or specific resistances e) highly diverse clones based on molecular markers Conduct regular review to remove non-essential materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
Limited storage space for clonal materials
[29 empty] | Untrained or inefficient personnel in sample processing | Reduction of good quality propagules and accidental mixtures | Conduct regular training and enforce close supervision of personnel on detection and removal of infected, infested and mechanically damaged samples. |  | Subculture samples of an accession in two steps (separated in time /different operator). Maintain spare cultures of the previous subculture cycle until new subcultures are established. |  | GRU
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
Untrained or inefficient personnel in sample processing
[29 empty] | Source of material is infected | Loss of viability of propagules |  | Provide an isolated growth room for in vitro explants taken directly from the field to allow time to detect insect infestations and disease infection and prevent their spread to other cultures. | Use material from virus-tested, virus-free plants. Indicate whether material is untested in the database records, so that virus elimination procedures can be initiated immediately. Conduct surface disinfestation with chlorine bleach (NaOCl 0.5 to 1% or commercial bleach 10-15%). Soak explants in a fungicide if fungal contaminants are likely. Additional treatments include short periods of sonication in NaOCl, double disinfection, oil sprays or dips, and insecticide treatment of mother plant before explants are taken. Wrap explants in plastic wrap during transport to help decrease spread of field organisms. | Obtain virus-free materials from other institutes as replacement accessions if virus testing or elimination are not available on-site. | GRU; Germplasm Health unit
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
Source of material is infected
[29 empty] | Poor quality and/or suboptimal size of propagule | Loss of meristems |  |  | Have additional materials available and change growth conditions to improve quality. Conduct experimentation to establish optimal meristem size for moderate growth and multiplication for each genus. |  | GRU
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
Poor quality and/or suboptimal size of propagule
[29 empty] | Weak mother plants | Short lifespan of propagules in storage |  |  | Collect plant material for tissue culture from vigorous and healthy mother plants. Improve in vitro introduction process. |  | GRU
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
Weak mother plants
[29 empty] | Ineffective pest and disease screening procedures during sample processing | Reduction of good quality propagules |  |  | If an isolation area is not available, new explants from the field should be wrapped and observed for mites and thrips for several subcultures. |  | GRU; Germplasm Health unit
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
Ineffective pest and disease screening procedures during sample processing
[29 empty] | No efficient tissue sterilisation procedures | Poor quality of propagules |  |  | Conduct research on tissue sterilisation for in vitro introduction.
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
No efficient tissue sterilisation procedures
[29 empty] | Lack of proper disposal procedures of contaminated plant materials | Increase in invitro contamination with pests and diseases and dissemination to new areas. |  |  | Autoclave all contaminated materials before discarding or cleaning vessels. Dispose in isolated areas. |  | GRU; Germplasm Health unit
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
Lack of proper disposal procedures of contaminated plant materials
[29 empty] | Ineffective thermotherapy procedure | Failure of explants to multiply |  |  | Conduct experimentation to establish thermotherapy procedure for propagules for moderate growth and multiplication for each genus. Treat materials sequentially in two groups. If the first group is damaged, change the protocol for the second group. |  | GRU
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
Ineffective thermotherapy procedure
[29 empty] | Inappropriate media and conditions for culture initiation | Failure of explants to multiply |  |  | Conduct experimentation to establish media composition and culture conditions for moderate growth and multiplication for each genus. Use a triage system and store only the best growing genotypes. |  | GRU
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
Inappropriate media and conditions for culture initiation
[29 empty] | Untrained personnel in health testing of propagules | Pest and disease damage and spread in collection | Train staff to be observant of unusual growth or symptoms in the cultures. |  |  |  | GRU; Germplasm Health unit
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
Untrained personnel in health testing of propagules
[29 empty] | Improper screening methods and monitoring regime | Pest and disease damage and spread in collection |  | Conduct regular monitoring of the cultures, storage rooms and growth room. Use a pyrethrum-based spray in culture rooms. Regularly check all sterilisation equipment and laminar air flow quality | Have a monitoring system for all contamination sources. Conduct bacteriogical testing of samples on a regular basis at initiation, during subculture and before storage and apply decontamination treatments. Remove and autoclave contaminated cultures, unless they are the only representatives of the germplasm. Handle infected cultures and potentially contaminated cultures at the end of the day to minimize spread of contamination. |  | GRU; Germplasm Health unit
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
Improper screening methods and monitoring regime
[29 empty] | Microbes and pests are not apparent at initial testing but appear later. | Pest and disease damage and spread in collection |  |  | Test at explant initiation and at one or two month intervals. |  | GRU; Germplasm Health unit
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
Microbes and pests are not apparent at initial testing but appear later.
[29 empty] | Untrained personnel in transgene detection | Loss of genetic integrity of other accessions |  |  |  |  | GRU/Biotechnology unit
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
Untrained personnel in transgene detection
[29 empty] | Inadvertent presence of transgene | Loss of genetic integrity of other accessions |  |  |  |  | GRU/Biotechnology unit
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
Inadvertent presence of transgene
[29 empty] | Lack or improper determination of transgene presence | Inaccurate or wrong information regarding transgene presence |  |  |  |  | GRU/Biotechnology unit
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
Lack or improper determination of transgene presence
[29 empty] | Limited quantity of high quality propagules | Loss of accession |  |  | Monitor plants in slow-growth storage every 3-4 months to assess their viability, for occurrence of necrosis, chlorosis, hyperhidricity, blackening, callus formation and defoliation. When the number of viable cultures of an accession drops to 3-12 or a certain percentage, or if the quality has drastically decreased, subculture the accession into a new set of fresh tissue cultures. Optimize slow growth process, monitor accession growth rate and plan successive subcultures. |  | GRU
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
Limited quantity of high quality propagules
[29 empty] | Ineffective sterilization techniques | Loss of accession |  |  | To decrease contamination spread, flame tools with 70% ethanol with additional 95% ethanol dip or prior soapy water dip if desired. Use hot bead sterilizers instead of alcohol lamps. |  | GRU
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
Ineffective sterilization techniques
[29 empty] | Misapplication of antibiotics | Loss of accession |  |  | Apply short (10 days) treatments in effective antibiotics in the growth medium to control bacterial contamination. Apply fungicide or use high-osmotic media to control fungal contamination. |  | GRU
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
Misapplication of antibiotics
[29 empty] | Somaclonal variation | Loss of genetic integrity |  |  | Use appropriate medium to assure genetic stability of in vitro collections. Monitor the plants for somaclonal variation, and grow abnormal plants to maturity in field or greenhouse to observe morphological changes. Genotypes prone to somaclonal variation should be monitored more closely. Develop molecular tools for somaclonal variation detection. Maintain DNA/dry leaf samples as reference samples for molecular integrity check. |  | GRU
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
Somaclonal variation
[29 empty] | Errors in media preparation | Loss of accession |  |  | Use specific protocols for each procedure and write down all steps to back track eventual errors if necessary. |  | GRU
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
Errors in media preparation
[29 empty] | Ineffective pre-treatment | Short lifespan of propagules in storage |  |  | Apply two weeks of growth on the storage medium in the normal growth room temperatures or apply cold acclimatization before placing in cold-storage. |  | GRU
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
Ineffective pre-treatment
[29 empty] | Chemical imbalance during culture | Abnormal growth of material |  |  | Check cultures for buildup of phenols, metabolites and browning in the medium and transfer as needed. Ensure proper hormone concentrations during propagation. Avoid high concentrations of cytokinins, which may affect genetic stability. |  | GRU
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
Chemical imbalance during culture
[29 empty] | Suboptimal culture methods for a broad range of genotypes |  |  |  | Conduct additional research to determine techniques suitable for a range of genotypes. |  | GRU
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
Suboptimal culture methods for a broad range of genotypes
[29 empty] | Short storage life of propagules | Loss of viability |  |  | Develop methods for extending the life of in vitro collections. Adjust osmotic pressure of in vitro samples to extend life rather than use hormones where there is a risk of genetic change. |  | GRU
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
Short storage life of propagules
[29 empty] | Delayed inventory | Loss of material |  |  | Schedule inventories based on the shortest period between which reculture is needed within the genus. |  | GRU
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
Delayed inventory
[29 empty] | Late subculturing | Loss of viability |  |  | Conduct regular monitoring to assess need for re-culturing as when the number of replicates has been reduced to 3-12. |  | GRU
Late subculturing
Late subculturing
Late subculturing
Late subculturing
Late subculturing
Late subculturing
Late subculturing
Late subculturing
Late subculturing
[29 empty] | Backlog in regeneration | Loss of viability |  |  | Periodically check viability and general performance of stored samples within recommended intervals. Back up accession with pot plants in the greenhouse if in vitro growth is experienced. |  | GRU
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
Backlog in regeneration
[29 empty] | Unsterile transfer facilities | Loss of accession |  | Design transfer facilities with minimal foot traffic and outside airflow. | Regularly check culture hoods for leaks with testing equipment (smoke) or with open bacteriological plates. Check for leaks whenever laminar flow hoods are moved. |  | GRU; Germplasm Health unit
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
Unsterile transfer facilities
[29 empty] | Unsuitable tissue culture containers for in vitro samples | Loss of accession |  |  | Carefully seal individual tissue culture containers of invitro samples with film against air-born contamination, pest attack and dessication. Culture replicates in separate TC containers to minimize container-specific risks. |  | GRU
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
Unsuitable tissue culture containers for in vitro samples
[29 empty] | Poor laboratory maintenance | Contamination and loss of materials | Field and greenhouse personnel should change their shoes and clothing before entering the lab and growth rooms. | Routinely mop floors with disinfectant. Control dust and insects, especially mites. Regularly change or clean filters in the laminar flow hoods and building's ventilation system. | Autoclave contaminated cultures before they are washed or remove them from the lab to a separate washing area. New explants should be held in a separate room or the lids wrapped with tape or plastic wrap until the possibility of insects is ruled out. Wipe cultures introduced from other laboratories with 70% alcohol or bleach and isolated from the main culture room until cleared of insect infestations. |  | GRU
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
Poor laboratory maintenance
[29 empty] | Safety duplication site is vulnerable to natural calamities | Inaccessible or loss of safety duplication |  |  | Store duplicates in at least two places for safety, either on-site in separate storage rooms or as black-box or active collection off-site. Establish a duplicate as base collection in liquid nitrogen (cryo). |  | GRU
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
[29 empty] | Regeneration failure | Loss of germplasm |  |  | Adhere strictly to standard in vitro regeneration procedure. |  | GRU
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
Regeneration failure
[29 empty] | Incorrectly identified material is stored | Wrong germplasm stored and distributed |  |  | Use only verified materials |  | GRU
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
Incorrectly identified material is stored
[29 empty] | Isolation of material is not done correctly, meristems are damaged and regrowth as callus | Increased chance of variation | Training of lab personnel |  |  |  | GRU
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
Isolation of material is not done correctly, meristems are damaged and regrowth as callus
[29 empty] | Chemical cryoprotectants injure plant cells during pre-treatment | Reduced viability during storage |  |  | Optimize procedure to minimize damage |  | GRU
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
Chemical cryoprotectants injure plant cells during pre-treatment
[29 empty] | Plants are sensitive to preculture method | Loss of viability |  |  | Choose another preculture technique |  | GRU
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
Plants are sensitive to preculture method
[29 empty] | Technique does not work for all plants in the collection | Gaps in collection |  |  | Plan to have several techniques available for use |  | GRU
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
Technique does not work for all plants in the collection
[29 empty] | Thawing/rewarming is done improperly | Underestimate of post-thaw regeneration rate | Training for staff |  | Have standard protocols in place. |  | GRU
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
Thawing/rewarming is done improperly
[29 empty] | Water bath may be contaminated | Damage to samples |  |  | Use sterile water in containers within the waterbath. |  | GRU
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
Water bath may be contaminated
[29 empty] | New material in cryo-collection is not viable | Loss of samples |  |  | Conduct viability testing during initial processing and have a written protocol for all aspects of regrowth (medium, temperature, light) |  | GRU
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
New material in cryo-collection is not viable
[29 empty] | Dewars may fail. | Damage to samples |  |  | Use alarm systems and duplicate materials in a separate dewar. |  | GRU
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
Dewars may fail.
[29 empty] | Unreliable supply of liquid nitrogen (LN) | Damage to samples |  |  | Ensure a reliable source of LN from specialized companies, local hospitals, industry or artificial insemination centres. Alternatively, a small LN manufacturing plant may be purchased. Use long-hold dewars and plan refills to ensure regular supply. |  | GRU/Purchasing
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
Unreliable supply of liquid nitrogen (LN)
[29 empty] | Rapid loss of LN in dewar | Damage to samples |  |  | Provide a wide-mouth dewar for holding samples during processing and a narrow-mouth, long-neck dewar fo long-term storage. Use a sensor for low Liq N, with automatic text/page to 2-3 key staff when limits are reached. Conduct regular checks and fill dewars regularly. Replicate samples between two dewars. |  | GRU
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
Rapid loss of LN in dewar
[29 empty] | Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals | Loss of biological stability |  |  | Follow instructions closely on use of cryocane and dewar. Group samples based on demand level. Make more replicates of samples under heavy demand. Store long-term samples separately from often used samples |  | GRU
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
Improper placement on cryocane and to multiple rewarming and cooling cycles during sample retrievals
[29 empty] | Compromised integrity of cryovials | Contamination and loss of biological stability |  |  | Use cryovials with additional level of security such as cap-threads, a silicone gasket, plastic cryosleeves, and polyethylene membrane sealants. |  | GRU
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
Compromised integrity of cryovials
[29 empty] | Insuffiicent number of stored propagules | Loss of germplasm |  |  | Determine the number of replicates for storage based on the survival rates achieved, crop type, speed of propagation and material available for storage. |  | GRU
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
Insuffiicent number of stored propagules
[29 empty] | Low initial quality of explants. | Short lifespan of germplasm in storage |  |  | Collect plant material for field culture from vigorous and healthy mother plants. |  | GRU
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
Low initial quality of explants.
[29 empty] | Improper conditioning and propagation of vegetative material | Short lifespan of germplasm in storage |  |  | Conduct immediate propagation, washing or disinfection, depending on the material. |  | GRU
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
Improper conditioning and propagation of vegetative material
[29 empty] | Failure in propagation and storage of propagules | Loss of germplasm |  |  | Group accessions based on general propagation procedures. Carry out research for genotypes that do not respond well to the general methods. Contact other facilities to obtain additional information on propagation of specific genotypes. |  | GRU
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
[29 empty] | Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials | Increased pathogen or pest population in the facility, thereby jeopardizing the health of other accessions in the collection as well as introducing new pest or diseases in new regions/countries. | Conduct regular training and enforce close supervision of personnel on proper disposal of contaminated materials. | If applicable, grow incoming and regeneration materials in screenhouse or in isolation away from large areas of local farms. Duplicate collection in two other sites, or keep an in vitro or a cryo set. | Subject regenerated material to usual phytosanitary testing. When new cuttings are established, incinerate the original plant and sterilize and discard the substrate. Monitor field regularly and immediately rogue diseased plants. Accessions with special vulnerability to particular diseases or pests may require special treatment such as being placed in screen or greenhouses or being treated for those diseases on a specific schedule. |  | GRU; Germplasm Health unit
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
Failure to detect and remove samples with pests and diseases and improper disposal of contaminated materials
[29 empty] | Ineffective screenhouse to control insects |  |  | Construct and manage screenhouses to prevent disease-carrying insects from entering. Workers and visitors should not enter the screenhouses after visiting field plots. The entryway into the screenhouses should have a set of two doors that should not be opened at the same time to reduce the entry of insects. Check screens and structures periodically to assure they remain insect proof. |  |  | GRU/ Physical Plant unit
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
Ineffective screenhouse to control insects
[29 empty] | Backlogs in pest and disease monitoring | Loss of field bank samples | Hire and train adequate personnel to regularly monitor pest and diseases. |  |  |  | GRU
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
Backlogs in pest and disease monitoring
[29 empty] | False positive and false negative results during plant health testing. | Loss of materials due to false positive results. Dissemination of diseased materials due to false negative results. |  |  | Repeat tests in case of doubt and have replicates to confirm and have more reliable results. |  | GRU; Germplasm Health unit
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
False positive and false negative results during plant health testing.
[29 empty] | Limited numbers of viable plants | Loss of germplasm |  |  | Keep 3 to 20 vegetative propagules per accession. |  | GRU
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
Limited numbers of viable plants
[29 empty] | Mechanical mixtures or invasive plants | Loss of genetic integrity |  |  | Monitor the plants for offtypes and remove immediately. |  | GRU
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
Mechanical mixtures or invasive plants
[29 empty] | Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases) | Loss of materials |  |  | Monitor the genebank regularly and plan regeneration in advance. |  | GRU
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
Late rejuvenation or multiplication (plants lost their physiologic vigour or accumulated pests and diseases)
[29 empty] | Inadequate selection, pre-conservation or pre-treatment of propagules | Poor plant establishment | Use trained personal and follow clear methodologies |  | Monitor all steps of sample preparation and take measures to avoid unecessary risks (plan the work to avoid interruptions and delays during weekends or hollidays). Prepare all materials in advance (chemicals, tools) |  | GRU
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
Inadequate selection, pre-conservation or pre-treatment of propagules
[29 empty] | Failure in propagation and storage of propagules | Loss of germplasm |  |  | Group accessions based on general propagation procedures and vegetative period. Carry out research for genotypes that do not respond well to the general methods. Contact other facilities to obtain additional information on propagation of specific genotypes. |  | GRU
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
Failure in propagation and storage of propagules
[29 empty] | Inadequate number of replicates per accession. | Loss of germplasm |  |  | Increase number of replicates per accession to represent the genetic variability of the accessions. |  | GRU
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
Inadequate number of replicates per accession.
[29 empty] | Unsuitable conditions in conservation site | Poor or suboptimal growth |  | Select a conservation site that is safe, favours plant development of the target germplasm, and isolated to prevent pest attacks and diseases but with easy access for management. Ensure that the climate and ecology of the site are conducive to maintenance. |  |  | GRU
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
Unsuitable conditions in conservation site
[29 empty] | High pest and disease pressure in field site | Loss of germplasm |  | Use screenhouse (SH) culture to provide the best protection against worst diseases, insects and pests. |  |  | GRU; Germplasm Health unit; Physical Plant unit
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
High pest and disease pressure in field site
[29 empty] | Pollen exchange with plants within and outside collection. | Loss of genetic integrity |  | Isolate site from potential pollinators if intended for outcrossing species. | Arrange the plants at good spacing distance to prevent plants from exchanging pollen. Bag reproductive structures and manage insect pollinators, or use individual mesh houses for each accession. Research needed on outcrossing rates of certain taxa can guide field layouting. |  | GRU
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
Pollen exchange with plants within and outside collection.
[29 empty] | Misidentification | Loss of germplasm |  |  | Develop field maps and use them during planting, evaluation and harvest. Record and identify with name and accession number all plants in the field on maps. Use weather resistant, and if possible, computer-generated labels. |  | GRU
Misidentification
Misidentification
Misidentification
Misidentification
Misidentification
Misidentification
Misidentification
Misidentification
Misidentification
[29 empty] | Mixtures of clones | Loss of genetic integrity |  |  | Provide adequate spacing between accessions taking into consideration the adult size growth habit of the plants. Plants that readily spread by rhizomes or runners may require wider spacing between plots to prevent clones from mixing. Accessions with different morphologies may be planted in adjacent plots when creeping or spreading is a problem. Particularly, invasive clones may require planting in cans, pots or boxes to reduce mixing or competition with less vigorous accessions. Prune plants if necessary. |  | GRU
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
Mixtures of clones
[29 empty] | Contamination with volunteer plants. | Loss of genetic integrity |  |  | Use adequate crop rotation system. Let volunteers grow after field preparation and remove them before planting new materials. |  | GRU
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
Contamination with volunteer plants.
[29 empty] | Mixtures of fruits and germplasms | Loss of genetic integrity |  |  | Conduct thinning and pruning to prevent overlapping between plants and mixtures of fruits and germplasms. |  | GRU
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
Mixtures of fruits and germplasms
[29 empty] | Poor adaptation | Loss of germplasm |  |  | Monitor collection frequently and transfer struggling accessions to possible alternative sites such as greenhouse or in vitro culture. Research is needed to study and understand the specific environmental requirements of different accessions in order to better manage them in field genebank. |  | GRU
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
Poor adaptation
[29 empty] | Disparate location of physiologically similar accessions | Inefficient management |  |  | Plant accessions in groups according to vigour, height, branching habit or lodging tendencies. Crops that must be harvested on a regular basis should be planted in groups by harvest dates or time to maturity. |  | GRU
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
Disparate location of physiologically similar accessions
[29 empty] | Poor management of weeds and low soil fertility | Loss of germplasm |  |  | Control weeds to limit competition and reduce weed-borne pathogens and insects. Monitor soil fertility and adjust as needed. |  | GRU
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
Poor management of weeds and low soil fertility
[29 empty] | Persistence of disease organisms and insects after harvest | Deterioration of propagules and spread of pests and diseases during storage |  |  | Treat tubers with fungicide and insecticide before storage. Closely monitor for bacterial and fungal infections, and immediately remove rotten tubers to prevent them from infecting other healthy tubers. |  | GRU; Germplasm Health unit
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
Persistence of disease organisms and insects after harvest
[29 empty] | Mishandling | Deterioration of propagules during storage |  |  | Take extreme care during harvest and transportation to avoid physical damage to tubers. |  | GRU
Mishandling
Mishandling
Mishandling
Mishandling
Mishandling
Mishandling
Mishandling
Mishandling
Mishandling
[29 empty] | Inefficient and erroneous data gathering and encoding | Backlog and inaccurate characterization data | Assign staff with adequate training in characterization following international standards. | Provide digital hand-held encoder. | Independently verify encoded data. Automate computing, updating and reporting of characterization data in database. |  | GRU
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
[29 empty] | Descriptors that have no clear-cut correspondence to current international standard descriptors | No or limited usefulness of characterization data |  |  | Use updated descriptors and provide references for all measurements and classifications. | Re-characterize accessions for problematic traits using current international standard descriptors. | GRU
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
[29 empty] | Limited text-based description | Incomplete and inaccurate morphological description |  |  | Include images (600-800 pixels) of key plant parts accompanied with standard color guide eg. Mansell colors. |  | GRU
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
[29 empty] | Lack of diversity assessment of collection | Unknown level of breadth, duplication and gaps in collection, and conservation of unnecessary duplicates |  |  | Conduct molecular profiling and diversity analysis | Determine a set of core collection and begin eliminating redundant duplicates of the core materials. | GRU
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
[29 empty] | Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty | Distribution without accompanying MTA. Inadvertent distribution of restricted germplasm (e.g. Non-MLS materials). Wrong information on the exchange status (MLS) of the germplasm. | Conduct regular update on international agreements concerning germplasm exchange. |  | Implement a clearance sheet for germplasm distribution ensuring appropriate MTA and other documents and approval of personnel concerned are obtained before release. | Immediately send correct documents and information to recipient of germplasm, including acknowledgment receipt and agreement forms to be completed and returned. | GRU; Plant Breeding; Training
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
Lack of knowledge or negligence on germplasm exchange Protocol and International Treaty
[29 empty] | Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm | Restrictions on future access and use of germplasm |  |  | Distribute accessions under a standard FAO-CGIAR MTA for “designated” germplasm, and for Center-created "non-designated" material developed in collaboration with FAO and other CGIAR Center, with a clause on the right of the Center to take legal action in case of violation of the MTA, upon recipient's agreement to MTA conditions. | Send a notice to patent and PVP offices about status of germplasm materials in question. File legal suit against violators and prohibit their access to IT germplasm. | GRU; Center Mgt; FAO
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
[29 empty] | Plant health restrictions of importing country | Low level of exchange and utilization of germplasm. |  |  | Conduct research on plant sanitation to facilitate germplasm exchange.
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
Plant health restrictions of importing country
[29 empty] | Non compliance with phytosanitary regulations | Germplasm distributed from genebank with diseases or pest contamination. |  |  | Test materials for bacterial and fungal diseases in compliance and germplasm health checks according to the phytosanitary standards of the importing country. Accompany outgoing material with an import permit from the requesting country and a phytosanitary certificate. | Immediately send disease and pest management procedures to recipients of germplasm. | GRU; germplasm Health
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
Non compliance with phytosanitary regulations
[29 empty] | Germplasm distributed are weak | Dissatisfied recipients of germplasm |  |  |  |  | GRU
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
Germplasm distributed are weak
[29 empty] | Misclassification and wrong characterization and germplasm stocks data | Delayed identification and preparation of requested germplasm | Conduct regular training on germplasm characterization. |  | Check characterization data specially the easily identifiable characters. Include evaluation data that relate to needs of the possible different users. Request all germplasm recipients within and outside Center to share their generated data related to the provided germplasm. | Acknowledge receipt of germplasm request. If there is reasonable doubt on identity and availability of requested germplasm, notify requester of possible delay of delivery pending confirmation of identity and availability. | GRU, Library, Communications Office
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
Misclassification and wrong characterization and germplasm stocks data
[29 empty] | Inefficient and slow processing of requests for samples. | Dissatisfied recipients of germplasm | Dedicate personnel to serving germplasm requests. |  | Keep files of relevant country and international quarantine documents . |  | GRU; germplasm Health
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
[29 empty] | Errors in preparing or labeling samples | Wrong germplasm distributed by the genebank |  |  | Adopt barcoding and closely adhere to germplasm distribution protocol. | Immediately send correct germplasm and instructions on disposing received wrong germplasm. Recipient should be required to send written confirmation of compliance with the disposal procedures. | GRU
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
[29 empty] | Insufficient germplasm stock for distribution | Delay in serving germplasm request |  |  | Incorporate alerts in the computerized germplasm stock control system to call attention to need for mutlipication and regeneration. Keep plenty of popular genetic stocks in the active set as well as their DNA samples if available. | Conduct germplasm mutliplication of the accessions concerned and notify requestor of expected date of germplasm availability. Make an agreement with requestor on funding and schedule of germplasm increase, if Center cannot immediately meet request. | GRU
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
Insufficient germplasm stock for distribution
[29 empty] | Bulky tissue-cultured explants | Expensive shipping cost and vulnerability of material to disintegration |  |  | Use space-saving growth bags with 2 layers of zip-up.
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
Bulky tissue-cultured explants
[29 empty] | Unfavorable conditions during transport | Delay in delivery , reduction of viability or loss of materials |  |  | Use packing materials that can withstand unfavorable conditions. Choose express delivery and under dry-ice if available. Use the safest shipment services with reliable tracking system. | If route and time taken by material are unreasonably extended, resend new germplasms using an alternative courier. | GRU
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
[29 empty] | Inefficient recording and database management | Backlog and inaccurate characterization data |  |  | Use GRU Database System and submit new data to SINGER every month. Bind hard copies of data in books. |  | GRU, IT unit
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
[29 empty] | Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation) | Loss or inaccessibility of information |  |  | Use GRU Database System and archive original data sheets. Integrate genebank operations, distribution records,and germplasm exchange policy databases. | Regularly monitor data handling and encode stray data. | GRU, IT unit
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
[29 empty] | Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data. | Inaccurate or wrong information |  |  | Independently verify encoded data. Automate computing, updating and reporting germplasm inventory, viability, storage location, and characterization data in database. Provide decision-making tools in the database for various genebanking operations. | Re-encode inventory and viability data from data sheets if reliable, otherwise repeat inventory and viability tests. | GRU
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
Improper recording of moisture content, germplasm inventory, viability, storage location, and characterization data.
[29 empty] | Lack of adequate information about important characteristics of each accession. | Low interest and utilization of germplasm |  |  | Collect data on important traits. Include desirable information from various sources. |  | GRU
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
Lack of adequate information about important characteristics of each accession.
[29 empty] | Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container. | Loss or misplacement of materials |  |  | Set up a standard protocol for labeling and placement of samples from registration to regeneration to harvesting. One label should follow an explant through the entire process. Use a mixture of letters and numbers to decrease the possibility of transposing numbers. Use a barcoding system to keep track of all accessions. Use preprinted labels to reduce human error. Use scanners and pocket PCs in data gathering. Use labeling that does not require continual rewriting of the label. Maintain lyophilized leaf samples of each accession as a reference for identification. |  | GRU
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
Mislabelling of new bags and other containers for the germplasm accession and samples are placed in the wrong container.
[29 empty] | Lack of secure back-up | Loss of genebank data |  | Transfer new data on CD or tape in two central databases kept in separate buildings in the institute. They can be stored also in secure, passport-regulated cyberspace. | Produce hard photocopy and electronic copy of original data sheets. Use automatic back-up on transaction computer after each session. Make daily incremental back-ups and weakly full back-ups. | Retrieve data from back-up electronic copies and /or paper records if available. Otherwise, conduct germplasm stock inventory and retake viability tests of materials, prioritizing the weakest germplasm types based on experience and literature. Hire necessary personnel to complete work as quickly as possible. | GRU, IT unit
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
[29 empty] | Important data and information remain in unuseful form. | Low level of utilization of germplasm and information. |  |  | Disseminate relevant information about germplasm and genebank operations by publishing in germplasm catalogs, newsletters, journals, bulletins, and operation manuals in print and cyber media. | Provide on-demand technical assistance for special data and information search about germplasm. | GRU, Library, Communications Office
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
[29 empty] | Outdated or inaccessible procedures manual | Loss of improvements in procedures |  |  | Write out in detail all procedures and recipes in a procedures manual as a reference guide for workers. Update the manual yearly or any time major procedure changes are instituted. |  | GRU
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
Outdated or inaccessible procedures manual
[29 empty] | Inconsistent protocols | Much variation in quality of process outputs |  |  | Develop standard protocols and recipes. Design media sheets as worksheets to minimize errors. When new protocols and recipes are developed, file the old ones for reference. |  | GRU
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
Inconsistent protocols
[29 empty] | Lack or complicated tracking and inventory system | Loss or misplaced samples and failure to regenerate and serve germplasm request on time |  |  | Design a computer inventory system that will allow researchers to follow each accession from acquisition through culture and storage. The system should include and link acqusition information, field data, image data and in vitro records for each accession. Include storage date, location in dewar, number of vials, number of meristems per vial, technique used, thawing technique required, recovery medium and other important procedures. |  | GRU
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
Lack or complicated tracking and inventory system
[29 empty] | Insufficient data on accession identity and culture conditions | Underestimate of germplasm viability or failure to propagate by recipient |  |  | Include each accession's explanting date, source, initiation medium, multiplication medium, rooting medium, growth information, experimental data, length of subculture, etc. Identify plants by the same numbering or labelling system as the field genebank to allow the plants to be traced back to the mother plant when necessary. |  | GRU
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
Insufficient data on accession identity and culture conditions
[29 empty] | Limited ICT capability; server, network and IT related problems | Lack or poor accessibility of germplasm and important data to potential users | Engage a competent data curator to document decades of evaluation data in a centralized database system. | Use stable software and hardware and engage full technical support from Information Technology Unit. Change computers every 5 years. Upgrade memory and operating system every year. | Regulate software installation and downloading. Restrict use of computer to authorized personnel. | Provide information request menu on the webpage and serve requests by digging print and/or electronic records. | GRU, IT unit
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
[29 empty] | Malfunctioning equipment, hardware and software problems | Failure to update data by genebank staff. Delays in recording of accessions and declaring them to FAO & SINGER |  | Install redundant UPS units and hot-swappable battery packages. Enforce automatic start-up of generator within 30 seconds. Use alternating 2 power-supplies connected to the same server. | Enable immediate notification of 2 staff at work and home phones in case of database-related problems. Back up data weekly to 2 tapes/CDs, 1 kept in Center, the other in staff’s home for 1 year and later in the international data hub. |  | GRU
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
Malfunctioning equipment, hardware and software problems
[29 empty] | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Reduction or loss of viability |  | Treat culture rooms with pesticides on a regular time basis. Regularly check and maintain cooling units. Maintain storage room conditions and monitor conditions daily via remote sensing devices. Install a High Efficiency Particle-removal Air system (HEPA) and alarm systems for open doors, temperature/ humidity changes in the culture areas. Provide a dehumidifier. | Conduct regular monitoring and cleanup to prevent fungus problems especially in tropical climates. Monitor MTS materials every 3-4 months for occurrence of necrosis, chlorosis, hyperhidricity, blackening, contamination, callus formation and defoliation. Develop in vitro diagnostic tools. | Multiply, carefully process and send accessions to better genebanks for safety back-up. | GRU, Physical Plant
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
[29 empty] | Poor organization of storage trays, shelves and compartments | Loss or misplacement of germplasm | Restrict storage facility access to authorized genebank personnel. | Rationalize arrangement of storage trays, shelves, and compartments. | Develop a simple labeling system for the storage space units. Conduct regular and independent verification of location of accession, and update it on computerized database system. |  | GRU
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
[29 empty] | Deterioration of facilities and equipment | Reduction or loss of viability |  | Pursue continual upgrading and expansion of field and laboratory equipment, etc. |  |  | GRU
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
[29 empty] | Cold room malfunction | Reduction or loss of viability |  | Place hygrothermographs that are connected to back-up power supply and alarm system. Provide the rooms with multiple compressors and dehumidifiers that are programmed for alternate operation. |  |  | GRU, Physical Plant
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
[29 empty] | Power supply cut-off | Reduction or loss of viability |  | Install, regularly check, and maintain an emergency electrical generator for back-up power to the storage rooms, essential genebank lighting, monitoring devices, and access locks during electrical power failures. |  |  | GRU, Physical Plant
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
[29 empty] | Theft or vandalism | Loss of germplasm |  | Place the building under 24-hr perimeter security surveillance. Link the alarm system by optical fiber with security office and police. Install double locks in sensitive areas and closed-circuit camera monitoring by guards. Install sensors for door contacts, glass breaks and unusual motion outside work hours. | Restrict access to genebank facilitites to authorized personnel with assigned badge and PIN code for access. Conduct background check on personnel who will use facility. Regularly brief security guards on the safety and security protocols of the genebanks. |  | GRU, Physical Plant, Security
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
[29 empty] | Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire | Reduction or loss of viability | Assign personnel from genebank unit and security office for 24/7 watch of the facility. | Design and construct building according to safety, environmental and artillery protection, and earthquake proof standards. Install automatic fire and gas alarm systems and provide fire isolation doors and fire extinguishers. Provide doors than can open from inside cold chambers to prevent personnel getting trapped. | Conduct periodic maintenance checks and inspect genebank during heavy rains and earthquakes for leaks in the cold and drying rooms. Periodically check fire safety checks. |  | GRU
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
[29 empty] | Safety duplication site is vulnerable to natural calamities | Inaccessible or loss of safety duplication |  | Establish duplicate back-up in a geologically secure site with low radiation (radioactivity) and stable (low probability of earthquakes). The facility must be situated at an altitude that guarantees proper drainage during seasonal rains and eliminates the risk of flooding in the event of rising sea levels due to global warming. |  |  | GRU
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
[29 empty] | Changing policies, financial and technical capabilities of governments hosting safety duplication | Inaccessible or loss of safety duplication |  | Establish safety backup arrangements in two different, economically stable countries, preferably in different continents, for black-box storage. Prepare a pull-out scheme in the event of instability in host country. Duplicate collection in two other sites, or keep an in vitro or a cryo set. |  |  | Center top mgt; SGRP; GRU
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
[29 empty] | Inadequate complement of technical staff | Inefficient operations | Hire at least one highly qualified technician each to manage germplasm viability test, germplasm drying and moisture test, germplasm health test, characterization and regeneration, data management, and germplasm distribution. For an active collection with research and development needs, hire a scientist to take charge of planning, research and analysis, a technician to take charge of daily operation of the laboratory, laboratory assistants for germplasm cleaning, germplasm processing and germplasm packaging, and field workers for germplasming, field-layout, screenhouse and field maintenance and harvesting. |  |  |  | GRU; HR unit
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
[29 empty] | Incompetent staff | Inefficient operations | Hire researchers with advanced degrees in plant physiology/genetics. Hire laboratory technicians with a background in plant science. Hire laboratory assistants with training in basic botany. Provide 1-2 weeks intensive on-site training for each new staff member on standardized laboratory and field protocols, followed by close supervision for as long as needed.
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
[29 empty] | Routine tasks and uncompetitive remuneration | Fast staff turnover | Rotate work assignments as much as possible or assigning special projects to laboratory assistants. Train each assistant to make medium, wash dishes, transfer cultures, check cultures for contaminants, do basic record keeping, and other required laboratory tasks. Educate workers on the mission of the facility to provide a morale boost and establish a research-oriented approach to work. |  |  |  | GRU
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
[29 empty] | Exposure to occupational hazards | Reduced manpower capability |  | Provide potective clothing, gloves and safety devices such as showers, eyewash and fire extinguishers. | Protect staff members from pesticide exposure, for example, by spraying during weekends. |  | GRU, Pest Control unit
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
[29 empty] | Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN. |  | LN safety considerations should be included in the training of all new staff. | Well-ventilated room; handling and storage dewars must be vented; skin and eyes must be protected with cold-resistant gloves, aprons, safety glasses and closed-top shoes. Only LN-resistant vessels and instruments guaranteed by the manufacturer should be exposed to its vapor and liquid phases. Install oxygen level sensors and self-contained breathing apparatus.Install door magnetic locks that automatically unlock during emergencies. | Enforce pal system when entering cryo tank area. Constantly monitor cryo tank area on closed-circuit tv. |  | GRU
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
Suffocation/asphyxiation and frostbite and cold injury from LN exposure. Mechanical injury incurred on explosion of a pressurized vessel containing LN.
[29 empty] | Inefficient human resources services | Delayed hiring of required manpower |  |  | Review and streamline hiring/recruitment protocol. |  | HR
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
[29 empty] | Inefficient purchasing and repair services | Delayed delivery/repair of required supplies and equipment |  |  | Review purchasing protocol to speed up requisition process. Keep spare parts for crucial pieces of equipment in stock (specially the ones not locally available), as a risk mitigation procedure (filters, batteries, lamps, fuses, sealing devices) | Tap equipment and supplies of partner organizations, for a fee if required, pending delivery of ordered equipment and supplies. | GRU
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
[29 empty] | High cost of genebank operations | Loss of donor and user support |  |  | Closely follow and seize funding opportunities with The Global Crop Diversity Trust and other funding donors. | Charge shipping fees to recipients of germplasm especially the private sector and well-funded public organizations. | GRU; Center mgt
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations